## Module Dashboard
Preckon - completion by module
Every feature verified against the codebase and the deployed database on 20 Aug 2026. Weighted: Done 1.0, Partial 0.5, Scaffolded 0.25, Missing 0.
Module | What it does | Features | Done | Partial | Missing | % Complete | Progress | Where it stands
TenderLogix | Tender engineering and bid orchestration | 18 | 5 | 7 | 6 | 47.2% | █████████░░░░░░░░░░░ | Lifecycle, bid decision and approval work end to end. Requirements-with-citation and the compliance matrix - the module's core promise - are only partly there.
DocLogix | CDE, document control and document intelligence | 14 | 1 | 4 | 9 | 23.2% | █████░░░░░░░░░░░░░░░ | Clause extraction is genuinely good. Everything that makes it a CDE - register, numbering, revisions, transmittals - does not exist. The Knowledge Graph roadmap depends on this module first.
DrawLogix | Drawing, design, BIM and drawing intelligence | 16 | 7 | 5 | 4 | 59.4% | ████████████░░░░░░░░ | The strongest module. Intake, viewer, takeoff, revision compare and the AI copilot all work. Recognition, IFC and clash are the gaps.
QuantLogix | Takeoff, quantities and BOQ | 11 | 5 | 3 | 3 | 59.1% | ████████████░░░░░░░░ | Measurement, BOQ and reconciliation are solid. Traceability stops at PCM objects because source_region does not exist.
CostLogix | Rates, estimating and commercial | 8 | 1 | 1 | 6 | 18.8% | ████░░░░░░░░░░░░░░░░ | Pricing works. Everything after award - budget, commitments, forecast, EVM - is not started.
ScheduleLogix | Scheduling and project time intelligence | 15 | 4 | 0 | 11 | 26.7% | █████░░░░░░░░░░░░░░░ | A real deterministic CPM engine exists. The migration-first mission - P6 import, calendars, baselines - is entirely unbuilt.
ProcureLogix | Packages, RFQs and procurement | 6 | 1 | 0 | 5 | 16.7% | ███░░░░░░░░░░░░░░░░░ | Package grouping works. RFQ, quotes and commitments are not started.
NarrativeLogix | Technical narrative and proposal writing | 3 | 2 | 1 | 0 | 83.3% | █████████████████░░░ | Small module, largely complete for what it claims.
Platform / Core | Identity, tenancy, audit, AI governance, operations | 39 | 15 | 3 | 21 | 42.9% | █████████░░░░░░░░░░░ | Trust foundations are strong: audit chain, tenant isolation, durable jobs, provenance. AI governance and enterprise ops are the gaps.
TOTAL | All modules | 130 | 41 | 24 | 65 | 41.2% | ████████░░░░░░░░░░░░ | Against the blueprints as written. These describe a platform the documents themselves budget a large team for.

## TenderLogix
TenderLogix - 47% complete
Tender engineering and bid orchestration. 18 features audited: 5 done, 7 partial, 6 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Lifecycle | Tender workspace and lifecycle states | Done | lifecycle.ts, pursuit.ts, project lifecycle endpoint; workflow.tenderlogix + 5 sub-workflows seeded. | - | P0 | -
Lifecycle | Bid / no-bid decision | Done | bid_decision artifact type; agent.bid_qualification; workflow.bidqualification. | - | P0 | -
Lifecycle | Bid approval gate | Done | bid_approval artifact type; agent.approval_prep; bid.approve permission on Owner role. | - | P0 | -
Intake | Tender document intake and summary | Done | tender_summary artifact type; agent.tender; workflow.classify. | - | P0 | -
Requirements | Requirements extraction with clause citation | Partial | spec_clause artifact type + agent.specification extract normative clauses. | Clauses are extracted but are not turned into tracked Requirement objects with owner, due date, response and status. | P0 | L
Requirements | Compliance matrix | Partial | compliance_item artifact type; agent.compliance and agent.compliance_lead. | No matrix view, no mandatory flag, no Requirement-Evidence-Response-Approval chain. | P0 | L
Scope | Scope breakdown and gap detection | Missing | None. | Specified-but-unpriced, drawing-without-BOQ and duplicate-scope detection all absent. | P1 | L
BOQ | Employer vs derived vs adopted quantity reconciliation | Done | boq/reconcile.ts - 4 verdicts, proportional tolerance with absolute floor, override trail. 27 tests. | Logic complete but NOT yet surfaced in the BOQ screen. | P1 | S
Clarifications | Clarification lifecycle | Partial | client_query artifact type; agent.clarification; workflow.clarificationloop. | No Draft-Review-Approved-Submitted-Answered-Impact-Closed state machine; impact assessment not enforced before close. | P1 | M
Addenda | Addendum intelligence and impact | Missing | None. | Unincorporated mandatory addendum must be a hard submission blocker. Not modelled at all. | P1 | L
Risk | Risk register and commercial positions | Partial | risk artifact type; agent.risk; agent.commercial; workflow.riskreview. | No assumptions/qualifications/exclusions register, no risk-adjusted margin. | P1 | M
Strategy | Bid strategy and scenarios | Missing | None. | Target/minimum margin, walk-away conditions, competitor assumptions absent. | P2 | M
Submission | Submission readiness score | Partial | submission.ts; lifecycle gates. | Weighted readiness exists; the separate HARD GATE (blockers) is not implemented. | P1 | M
Submission | Submission builder and manifest | Partial | proposal_doc artifact type; agent.proposal; workflow.bidassembly. | No manifest validation (revision, signature, naming, format, addendum acknowledgement); no revision freeze at submission. | P1 | M
War Room | Tender War Room cockpit | Partial | surfaces/tender.tsx; project dashboards. | No countdown, readiness tiles, blocker list or AI brief. | P2 | M
Negotiation | Negotiation / BAFO revisions | Missing | None. | - | P2 | M
Award | Award / loss capture and win-loss analytics | Missing | None. | - | P2 | M
Handover | Bid-to-project handover | Missing | None. | Award should transfer to downstream modules with no re-keying. | P2 | L

## DocLogix
DocLogix - 23% complete
CDE, document control and document intelligence. 14 features audited: 1 done, 4 partial, 9 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Repository | File storage and versioning | Partial | file, file_page tables; upload and retrieval endpoints. | Plain file store. No controlled-vs-uncontrolled distinction, no folder or metadata views. | P0 | M
Register | Intelligent document register (35+ controlled fields) | Missing | document artifact type exists but is an AI output, not a controlled register record. | The core object of the module. No document number, discipline, originator, suitability, status or distribution. | P0 | L
Numbering | Document numbering engine | Missing | None. | No configurable schemes, segment validation, auto-increment, reserved ranges or duplicate detection. | P0 | M
Revisions | Formal revision vs file version | Missing | None. | No current/superseded semantics, no purpose-of-issue, no immutable superseded revisions. | P0 | M
Revisions | Revision intelligence (change classification) | Partial | cad/compare.ts diffs DXF revisions; cad/impact.ts gives affected/unaffected/unknown verdicts. 39 tests. | Works for CAD only. No document or text revision comparison, no change classification taxonomy. | P1 | L
Workflow | Configurable document workflow | Partial | workflow, workflow_run, workflow_run_step tables; workflow.doclogix seeded. | Generic engine only. No document states (WIP-Shared-Approved-IFC-Superseded), no SLA, escalation or approval matrices. | P1 | L
Review | Review and approval workspace | Partial | review-queue endpoints; deviations approve/reject. | No three-panel document review UI, no markup, no comments pinned to a region, no decision log. | P1 | L
Transmittals | Transmittal management | Missing | None. | Transmittals are a formal contractual record with acknowledgements. Entirely absent. | P0 | L
Extraction | Specification clause extraction | Done | spec_clause artifact type; agent.specification; surfaces/specs.tsx. | Genuinely working and the module's strongest feature. | P0 | -
Extraction | OCR for scanned documents | Missing | CAD extraction service handles drawings only. | No OCR for scanned PDFs, Office formats, email or images. | P1 | L
Search | Semantic / natural-language project search | Scaffolded | chunk table exists with embedding column and FULLTEXT index. | NOTHING reads or writes chunk. No ingestion, chunking, embedding or retrieval code exists. | P0 | L
Provenance | Document-region provenance anchor | Missing | artifact_provenance and trace endpoints exist but anchor to artifacts, not document regions. | source_region (page + polygon) is the linchpin for click-a-quantity-see-the-clause. Claimed in 4 documents. | P0 | M
Distribution | Distribution lists and controlled issue | Missing | None. | - | P1 | M
Retention | Retention categories and legal hold | Missing | None. | Enterprise records requirement. | P1 | M

## DrawLogix
DrawLogix - 59% complete
Drawing, design, BIM and drawing intelligence. 16 features audited: 7 done, 5 partial, 4 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Intake | DWG / DXF / PDF intake | Done | cad_extraction, file_page; Python sidecar with LibreDWG dwg2dxf; SVG render pipeline. | - | P0 | -
Intake | IFC import and export | Missing | None. | IFC is the open-BIM requirement named in three documents. No import or export at all. | P1 | L
Viewer | Drawing viewer with pan, zoom, layers | Done | cad/editor.tsx, cad/viewport.tsx; 31 sheets live in production. | - | P0 | -
Recognition | Symbol and object recognition to PCM candidates | Missing | Extraction produces geometry and text, not classified construction objects. | No recognition of walls, doors, windows, columns or rooms with confidence and a verification queue. | P1 | XL
Authoring | 2D drafting and editing | Partial | cad/editor.tsx with measure, iso views, roundtrip to DXF. | No trim/extend/offset/fillet/array; no hatch or leader tooling. | P2 | L
Authoring | 3D / BIM authoring | Partial | bim/studio.tsx, bim/model.ts, bim/iso.tsx. | No true parametric BIM authoring; no slabs, roofs, stairs, curtain walls. | P2 | XL
Commands | Deterministic command set | Partial | bim/commands.ts, cad/tools.ts; generic ToolRegistry with propose and apply. 108 tests across registry, tools and documentation. | Missing CreateSlab, Beam, Grid, Pipe, Duct, CreateView, CreateSheet, GenerateSchedule. | P1 | L
AI | AI Design Copilot with execution modes | Done | bim/agent2.ts, cad/agent.ts, cad/assistant route; discover-read-resolve-propose-review-apply-audit. | Matches the blueprint execution-mode model closely. The strongest AI surface in the product. | P0 | -
AI | Authored tools (user-defined automation) | Done | bim/authoring.ts, bim_authored_tool table, authoring-panel.tsx; steps are data, never code. | - | P1 | -
Revisions | Revision comparison and impact | Done | cad/compare.ts (content matching, adaptive tolerance) and cad/impact.ts. 39 tests. | - | P0 | -
Documentation | Sheets, tags, dimensions | Partial | bim/sheets.tsx, bim/documentation.ts. 29 tests. | No live schedules as PCM projections, no revision clouds, no sheet sets or issue packages. | P2 | L
Coordination | Clash and clearance detection | Missing | None. | No model federation, no clash workflow. | P2 | XL
Components | Smart components and families | Missing | library_entry table exists for reusable content. | No parametric component definitions with parameters, connectors, constraints or quantity rules. | P2 | L
Takeoff | Drawing-to-quantity measurement | Done | bim/takeoff.ts, cad/measure.ts, drawing_measurement artifact type with source_layers. | - | P0 | -
Validation | Standards and rule validation | Done | standards.ts, validate.ts; standard_violation artifact type; validate and violations endpoints. | - | P1 | -
Desktop | Desktop Studio client | Partial | Electron shell; desktop.ts, desktopBuilds.ts, bundles.ts; signed installers served from /desktop. | No native geometry runtime, no local PCM cache, no GPU renderer, no offline working package. | P2 | XL

## QuantLogix
QuantLogix - 59% complete
Takeoff, quantities and BOQ. 11 features audited: 5 done, 3 partial, 3 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Measurement | Measurement engine | Done | pcm/measure.ts, pcm/units.ts; drawing_measurement artifact type. | - | P0 | -
Measurement | Configurable measurement rules | Missing | Measurement logic is in code, not data. | No measurement_rule table, no versioned rule expressions, no standard references (NRM, POMI, CESMM). | P1 | L
BOQ | BOQ generation from measurements | Done | boq_line artifact type; agent.boq; workflow.quantlogix; surfaces/boq.tsx. | - | P0 | -
BOQ | BOQ export (csv, xlsx) | Done | boq/export.csv and boq/export.xlsx endpoints; xlsx-brand.ts. | - | P1 | -
BOQ | BOQ roster and rate application | Done | boq/roster and boq/rate endpoints; boq/pipeline.tsx. | - | P0 | -
Reconciliation | Multi-source quantity reconciliation | Done | boq/reconcile.ts - modelled vs measured vs manual, 4 verdicts, override trail. 27 tests. | Not yet wired into the BOQ surface, so estimators cannot see disputes. | P1 | S
Traceability | BOQ line to source object trace | Partial | pcm_boq_map, pcm_quantity, artifact_provenance, /artifacts/[id]/trace and /pcm/objects/[oid]/trace. | Trace reaches PCM objects but not the drawing region that produced them (no source_region). | P0 | M
Traceability | Click a quantity, highlight contributing objects | Missing | - | The headline traceability claim in four documents. Blocked on source_region. | P0 | M
Revision | Quantity dirty propagation and remeasure | Partial | pcm_quantity has a status column; cad/impact.ts identifies affected measurements. | Dirty-mark, queue, recompute pipeline is not wired end to end. Stale quantities can be displayed as current. | P1 | M
Revision | BOQ delta between revisions | Partial | cad/compare.ts produces the geometry delta. | No BOQ-level delta report or baseline preservation. | P1 | M
Assemblies | Assemblies and composite items | Missing | None. | - | P2 | M

## CostLogix
CostLogix - 19% complete
Rates, estimating and commercial. 8 features audited: 1 done, 1 partial, 6 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Rates | Rate library | Partial | library_entry table; library endpoints; cost_line artifact type; agent.cost. | No structured rate book with build-ups, regions, currencies or effective dates. | P1 | M
Estimate | Estimate generation and pricing | Done | cost_line artifact type; agent.cost; workflow.costlogix; surfaces/estimate.tsx. | - | P0 | -
Estimate | Estimate scenarios (base, target, BAFO) | Missing | None. | TenderLogix governs revisions and scenarios; none exist. | P1 | M
Commercial | Margin waterfall and markups | Missing | None. | No preliminaries, overhead, escalation, contingency, risk allowance, profit or tax breakdown. | P1 | M
Budget | Budget, commitments, forecast | Missing | None. | Cost control after award is not started. | P2 | XL
EVM | Earned value (PV, EV, AC, SPI, CPI) | Missing | None. | Requires schedule and cost integration. | P2 | XL
Cashflow | Cash flow and S-curves | Missing | None. | - | P2 | L
Change | Variation and change pricing | Missing | None. | No ChangeLogix module exists. | P2 | XL

## ScheduleLogix
ScheduleLogix - 27% complete
Scheduling and project time intelligence. 15 features audited: 4 done, 0 partial, 11 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Engine | Deterministic CPM engine | Done | cpm.ts - forward and backward pass, FS/SS/FF/SF with lag, total float, critical path. | Genuinely deterministic and the AI is kept out of the arithmetic, exactly as the blueprint requires. | P0 | -
Model | Activities and programme storage | Done | project_programme table; schedule_activity artifact type; agent.schedule; workflow.schedulelogix. | - | P0 | -
UI | Gantt and activity grid | Done | programme/gantt.tsx; surfaces/schedule.tsx; programme endpoints. | No frozen columns, bulk edit, saved layouts or network diagram. | P0 | -
Export | Programme export | Done | programme/export.xlsx. | - | P1 | -
Calendars | Global, project and resource calendars | Missing | None. | P0 in the ScheduleLogix matrix (SL-P6-009). CPM without calendars cannot reconcile with P6. | P1 | L
Migration | P6 XER import | Missing | None. | RELEASE-BLOCKING (SL-P6-001). The module's stated mission is migration-first. | P1 | XL
Migration | P6 XML import | Missing | None. | RELEASE-BLOCKING (SL-P6-002). | P1 | XL
Migration | Reconciliation and migration confidence score | Missing | None. | Appendix B requires a signed-off reconciliation package, not an Import Successful message. | P1 | L
Baselines | Baselines and schedule versions | Missing | None. | P0 (SL-P6-023, 024). No baseline compare or immutable published snapshots. | P1 | L
Progress | Progress, data date, percent complete | Missing | None. | P0 (SL-P6-015, 017, 018). | P1 | L
Resources | Resources, roles, histogram, levelling | Missing | None. | P1 tier (SL-P6-025, 033, 034). | P2 | XL
Look-ahead | Look-ahead and work readiness | Missing | None. | Named differentiator; depends on connected procurement and drawing data. | P2 | L
Intelligence | Schedule health scoring | Missing | None. | - | P2 | M
Intelligence | Delay intelligence and recovery scenarios | Missing | None. | Named the key differentiator in section 30. | P2 | XL
Intelligence | What-if sandbox | Missing | None. | - | P2 | L

## ProcureLogix
ProcureLogix - 17% complete
Packages, RFQs and procurement. 6 features audited: 1 done, 0 partial, 5 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Packages | RFQ package grouping by trade and lead time | Done | procurement_package artifact type; agent.procurement; workflow.procurelogix; surfaces/procurement.tsx. | - | P0 | -
RFQ | RFQ issue and vendor management | Missing | None. | No vendor master, no RFQ documents, no issue tracking. | P1 | L
Quotes | Quotation capture and comparison | Missing | None. | No bid levelling or comparison grid. | P1 | L
Coverage | RFQ coverage and gap flags | Missing | None. | Single source, expiry, scope exclusion and missing package flags absent. | P1 | M
Commitments | Purchase orders and commitments | Missing | None. | - | P2 | XL
Delivery | Delivery tracking and long-lead alerts | Missing | None. | - | P2 | L

## NarrativeLogix
NarrativeLogix - 83% complete
Technical narrative and proposal writing. 3 features audited: 2 done, 1 partial, 0 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Drafting | Technical narrative sections | Done | narrative_section artifact type; agent.narrative; workflow.narrativelogix; surfaces/narrative.tsx. | - | P1 | -
Export | Narrative export to markdown | Done | narrative/export.md endpoint. | - | P1 | -
Evidence | Narrative grounded in project evidence | Partial | Sections reference artifacts. | No retrieval layer, so grounding is limited to what is passed in the envelope. | P1 | M

## Platform-Core
Platform / Core - 43% complete
Identity, tenancy, audit, AI governance, operations. 39 features audited: 15 done, 3 partial, 21 missing.
Area | Feature | Status | Evidence in code / DB | Gap - what is still needed | Priority | Effort
Identity | Authentication | Done | Better Auth; account, session, user, verification tables; rate limit on sign-in. | - | P0 | -
Identity | SSO (SAML / OIDC) | Missing | None. | Enterprise deal blocker. Named in Complete Platform section 15. | P0 | L
Identity | MFA | Missing | Only i18n strings exist; no implementation. | Enterprise deal blocker. | P0 | L
Identity | SCIM provisioning | Missing | None. | - | P1 | M
Tenancy | Multi-tenant isolation | Done | tenant scoping on every query; tenancy.test.ts and tenant-scoping.test.ts (static analysis of every SQL statement). | MySQL has no RLS, so the app layer is the only line. The static-analysis test is the compensating control. | P0 | -
Tenancy | Tenant provisioning and custom domains | Done | tenant_bootstrap, tenant_domain, tenant_invite; provisioning.ts, domains.ts; domain provision endpoints. | - | P0 | -
AuthZ | RBAC roles and permissions | Done | tenant_role, tenant_permission, tenant_role_permission, user_role; iam.ts; 6 seeded roles. | No attribute-based rules (per-package subcontractor access). | P0 | -
Audit | Tamper-evident audit chain | Done | audit_event + audit_chain hash chain; /api/v1/audit and /audit/verify; chain.ts. | - | P0 | -
Provenance | Artifact provenance and review queue | Done | artifact, artifact_type, artifact_provenance with JSON-schema validation; confirm, reject and trace endpoints. | - | P0 | -
Workflow | Workflow and run engine | Done | workflow, workflow_run, workflow_run_step; run_deviation with approve and reject. | - | P0 | -
Jobs | Durable AI job queue | Done | ai_job with idempotency_key; job-queue.ts conditional-UPDATE claims, leases, backoff, reconciler. 21 tests. | - | P0 | -
Jobs | Per-attempt usage ledger | Missing | ai_job holds one MUTABLE row per job. | A retry overwrites the previous attempt tokens, so failed-attempt spend is invisible and AI cost is under-counted today. | P0 | S
AI Gov | Tenant AI policy and data sensitivity | Missing | No sensitivity field anywhere in src. | Blocks Preckon Private AI and Sovereign AI as sellable products. | P0 | L
AI Gov | Model registry and aliases | Missing | Model names hard-coded in 3 routes and jobs.ts. | Application code must reference aliases, not claude-opus-4-8. | P1 | M
AI Gov | Prompt registry with versions | Missing | Prompts are strings in worker/src/prompts.mjs. | AI Fabric section 18 forbids untracked prompt strings in source. | P1 | M
AI Gov | Budgets (token, cost, latency) | Missing | None. | Router must reject or re-route when a budget would be exceeded. | P1 | M
AI Gov | Response cache (exact, semantic, artifact) | Missing | None. | No cache layer of any kind. | P1 | L
AI Gov | Retrieval / RAG | Scaffolded | chunk table with embedding column and FULLTEXT index. | Nothing reads or writes it. Retrieval is schema-only. | P0 | L
Events | Transactional outbox | Done | event_outbox and usage_outbox tables. | No published event catalog or schema versioning. | P0 | -
Observability | Structured logging | Done | log.ts - request ids, AsyncLocalStorage context, key-based redaction. 21 tests. | - | P1 | -
Observability | Metrics, tracing, dashboards | Missing | trace_id exists on ai_job but no OpenTelemetry. | No metrics endpoint, no dashboards, no alerting. | P1 | M
FinOps | AI cost reporting | Partial | ai-cost.ts; /api/v1/ai-cost. 19 tests. | Built on under-counted data until the per-attempt ledger exists. | P0 | S
Entitlements | Modules, plans and entitlements | Done | entitlement_snapshot, entitlements.ts, modules.ts; internal entitlements endpoint. | - | P1 | -
UX | Design system, WCAG 2.2 AA | Done | globals.css semantic tokens with computed contrast; design-system.test.ts (24 tests). | - | P1 | -
UX | Internationalisation EN / AR / FR with RTL | Done | i18n/en, ar, fr; logical CSS properties; technical content not mirrored. | - | P1 | -
UX | Light, dark and system themes | Done | Alias token layer; system bootstrap in layout.tsx. | - | P1 | -
Ops | CI running the test suite | Missing | Six workflow files exist; none has ever executed (PAT lacks workflow scope). | 426 tests and six quality gates run only on a developer machine. | P0 | S
Ops | Automated backup and tested restore | Missing | None. | An untested restore is not a backup. | P0 | M
Ops | Staging environment | Missing | Production only. | Changes are currently validated in production. | P0 | M
Ops | Branch protection and PR review | Missing | autosync commits directly to main. | No review gate on production code. | P0 | S
Ops | Repeatable deploy | Done | deploy.ps1 - sha256-verified resumable upload, migrations, catalog seed gate, worker rebuild. | - | P0 | -
Security | Encryption at rest and key management | Missing | None. | Named in Complete Platform section 15. | P0 | L
Security | Secrets management (Vault / KMS) | Missing | Secrets in .env on the host. | - | P1 | M
Security | Credential rotation | Missing | Outstanding from the earlier security review. | Rotate everything ever committed; confirm the production DB password is not the default. | P0 | S
Security | Upload malware scanning | Missing | None. | - | P1 | M
Security | Port hardening | Partial | 3308, 4000 and 8081 bind to 127.0.0.1 and are externally closed. | 3307 (MySQL), 11434 (Ollama, unauthenticated) and 5000 bind 0.0.0.0; only the provider firewall stops them. | P0 | S
Governance | Architecture Decision Records | Missing | No docs/adr directory. | 50 ADRs are specified across three blueprints. Zero exist. | P1 | M
Integration | Enterprise Integration Hub and connector SDK | Missing | integrations.ts is stub-level. | No connector runtime, canonical mapping or reconciliation engine. | P2 | XL
Knowledge | Cross-module knowledge graph | Partial | pcm_relationship with typed edges, source and confidence. | PCM-scoped only. No Doc-Draw-Quant-Cost-Schedule traversal, no lineage or downstream-impact APIs. | P1 | XL

## P0 Backlog
Everything marked P0, across all modules
These block enterprise readiness or are actively wrong today. Sorted by module.
Module | Feature | Status | Why it blocks | Effort | Priority
TenderLogix | Requirements extraction with clause citation | Partial | Clauses are extracted but are not turned into tracked Requirement objects with owner, due date, response and status. | L | P0
TenderLogix | Compliance matrix | Partial | No matrix view, no mandatory flag, no Requirement-Evidence-Response-Approval chain. | L | P0
DocLogix | File storage and versioning | Partial | Plain file store. No controlled-vs-uncontrolled distinction, no folder or metadata views. | M | P0
DocLogix | Intelligent document register (35+ controlled fields) | Missing | The core object of the module. No document number, discipline, originator, suitability, status or distribution. | L | P0
DocLogix | Document numbering engine | Missing | No configurable schemes, segment validation, auto-increment, reserved ranges or duplicate detection. | M | P0
DocLogix | Formal revision vs file version | Missing | No current/superseded semantics, no purpose-of-issue, no immutable superseded revisions. | M | P0
DocLogix | Transmittal management | Missing | Transmittals are a formal contractual record with acknowledgements. Entirely absent. | L | P0
DocLogix | Semantic / natural-language project search | Scaffolded | NOTHING reads or writes chunk. No ingestion, chunking, embedding or retrieval code exists. | L | P0
DocLogix | Document-region provenance anchor | Missing | source_region (page + polygon) is the linchpin for click-a-quantity-see-the-clause. Claimed in 4 documents. | M | P0
QuantLogix | BOQ line to source object trace | Partial | Trace reaches PCM objects but not the drawing region that produced them (no source_region). | M | P0
QuantLogix | Click a quantity, highlight contributing objects | Missing | The headline traceability claim in four documents. Blocked on source_region. | M | P0
Platform / Core | SSO (SAML / OIDC) | Missing | Enterprise deal blocker. Named in Complete Platform section 15. | L | P0
Platform / Core | MFA | Missing | Enterprise deal blocker. | L | P0
Platform / Core | Per-attempt usage ledger | Missing | A retry overwrites the previous attempt tokens, so failed-attempt spend is invisible and AI cost is under-counted today. | S | P0
Platform / Core | Tenant AI policy and data sensitivity | Missing | Blocks Preckon Private AI and Sovereign AI as sellable products. | L | P0
Platform / Core | Retrieval / RAG | Scaffolded | Nothing reads or writes it. Retrieval is schema-only. | L | P0
Platform / Core | AI cost reporting | Partial | Built on under-counted data until the per-attempt ledger exists. | S | P0
Platform / Core | CI running the test suite | Missing | 426 tests and six quality gates run only on a developer machine. | S | P0
Platform / Core | Automated backup and tested restore | Missing | An untested restore is not a backup. | M | P0
Platform / Core | Staging environment | Missing | Changes are currently validated in production. | M | P0
Platform / Core | Branch protection and PR review | Missing | No review gate on production code. | S | P0
Platform / Core | Encryption at rest and key management | Missing | Named in Complete Platform section 15. | L | P0
Platform / Core | Credential rotation | Missing | Rotate everything ever committed; confirm the production DB password is not the default. | S | P0
Platform / Core | Port hardening | Partial | 3307 (MySQL), 11434 (Ollama, unauthenticated) and 5000 bind 0.0.0.0; only the provider firewall stops them. | S | P0

## Evidence
What exists - counted, not assumed
Queried from the repository and the deployed production database.
Area | Count | Detail
Modules seeded | 8 | tenderlogix, drawlogix, doclogix, quantlogix, costlogix, schedulelogix, narrativelogix, procurelogix
Artifact types | 18 | bid_approval, bid_decision, boq_line, client_query, compliance_item, cost_line, document, drawing_index, drawing_measurement, narrative_section, procurement_package, proposal_doc, rfi, risk, schedule_activity, spec_clause, standard_violation, tender_summary
AI agents | 20 | approval_prep, bid_qualification, boq, clarification, commercial, compliance, compliance_lead, construction_copilot, cost, document, drawing, knowledge, narrative, procurement, proposal, rfi, risk, schedule, specification, tender
Workflows | 14 | One per module plus 6 TenderLogix sub-workflows (classify, riskreview, clarificationloop, bidqualification, bidassembly, skeleton)
Database tables | 56 | Includes 12 pcm_* tables, artifact + provenance, audit_event + audit_chain, event_outbox, ai_job
API routes | 78 | Next.js App Router handlers under src/app/api
Module surfaces | 10 | boq, drawings, estimate, narrative, procurement, schedule, specs, tender, common, generic
Tests | 426 passing | 23 files plus Playwright golden-path E2E. One pre-existing failure needs Docker MySQL on 3308.
Deterministic engines | 7 | cpm.ts, pcm/measure.ts, boq/reconcile.ts, cad/compare.ts, cad/impact.ts, standards.ts, validate.ts
Live sheets in production | 31 | Average 8.1 MB, largest 37 MB - a real performance concern for the drawing editor
Deployed versions | next 15.5.23 | postcss 8.5.26 - both verified inside the running container
CI runs | 0 | Six workflow files exist; none has ever executed
ADRs | 0 | 50 are specified across three blueprints