## Read Me
Preckon - Blueprint vs Implementation
Every row verified against the codebase on 19 Aug 2026. Nothing here is inferred from the documents alone.
What this compares | All 10 documents in Preckon-system/Documents/ against the deployed preckon-tenant codebase.
Sheets
2. Scorecard | Completion by document, with a weighted readiness figure.
3. Comparison | The detailed requirement-by-requirement audit. 100 rows. Start here.
4. Enterprise Readiness | Security, operations and compliance controls an enterprise buyer will ask about.
5. Document Conflicts | Places the documents contradict each other. Read this before planning work.
6. Roadmap | P0 items only, sequenced. What to actually do next.
7. Built Inventory | Raw evidence: tables, routes, engines, tests.
Status meanings
Done | Implemented and verified in code.
Partial | Real implementation exists but does not meet the full requirement.
Scaffolded | Database or config exists but NO code reads or writes it. Looks built; is not.
Missing | No implementation.
N/A | Document specifies something the implementation deliberately does not do. See Conflicts.
Priority
P0 | Blocks enterprise readiness, or is actively wrong today.
P1 | Needed for a credible enterprise product.
P2 | Differentiator or later phase.
Effort | S = days. M = 1-3 weeks. L = 1-2 months. XL = a quarter or more, usually needs a team.
Headline | The build is strong where it matters most for trust - AI cannot commit business state, the audit chain is tamper-evident, tenant isolation is tested, and the deterministic engines (CPM, measurement, reconciliation) are real. The gaps are concentrated in DocLogix (essentially unbuilt), AI governance (no policy, no per-attempt ledger), and operations (CI has never run).

## Scorecard
Completion by document
Weighted: Done = 1.0, Partial = 0.5, Scaffolded = 0.25, Missing = 0. N/A rows excluded.
Document | Requirements audited | Done | Partial | Scaffolded | Missing | Weighted complete | Verdict
AI Fabric | 21 | 4 | 4 | 1 | 12 | 29.8% | Contracts and job durability are solid; governance, retrieval and caching are absent.
PCM | 21 | 11 | 1 | 0 | 8 | 57.5% | Core object and change model built. Property schema, types, classification and source_region missing.
DocLogix | 9 | 0 | 3 | 0 | 6 | 16.7% | Effectively unbuilt, and the Knowledge Graph roadmap depends on it first.
DrawLogix | 9 | 2 | 5 | 0 | 2 | 50% | Strongest AI surface in the product. Recognition, IFC and clash are the gaps.
DrawLogix Studio | 3 | 0 | 1 | 0 | 2 | 16.7% | Ships as an Electron shell. Native runtime, offline and sync are not started.
TenderLogix | 7 | 1 | 2 | 0 | 4 | 28.6% | Reconciliation is done and good. Requirements extraction - the recommended first AI workload - is not started.
ScheduleLogix | 9 | 2 | 0 | 0 | 7 | 22.2% | Real CPM engine exists. P6 migration, calendars and baselines are the release blockers.
Knowledge Graph | 4 | 0 | 2 | 0 | 2 | 25% | Impact logic exists for CAD only. Cross-module traversal not started.
Master | 13 | 5 | 4 | 0 | 3 | 58.3% | Platform rules are honoured. Governance artefacts (ADRs, PRA) do not exist.
TOTAL | 96 | 25 | 22 | 1 | 46 | 38.6% | Against the documents as written. Weighted for partial credit.

## Comparison
Requirement-by-requirement comparison
Evidence column cites the actual file or table. Gap column says what is needed, not merely that something is absent.
Document | Ref | Requirement | Status | Evidence in code | Gap / what is needed | Priority | Effort
AI Fabric | P-01 | No module calls a model provider directly | Done | API routes enqueue ai_job; only worker/src calls a provider. | Add a CI lint that fails if a provider SDK is imported outside worker/. | P1 | S
AI Fabric | P-02 / 51.13 | AI cannot commit authoritative business state | Done | propose-review-apply; bim_proposal, artifact_provenance, audit_chain, confirm/reject routes. | None. Strongest part of the build. | P0 | -
AI Fabric | P-03 | Deterministic before probabilistic | Partial | cpm.ts, pcm/measure.ts, boq/reconcile.ts, cad/compare.ts are deterministic engines. | No deterministic task REGISTRY the router consults before calling a model. | P1 | M
AI Fabric | P-04 / 11 | Retrieval before long context | Scaffolded | chunk table exists with embedding JSON and FULLTEXT index. | NOTHING reads or writes chunk. No ingestion, chunking, embedding or retrieval code. | P0 | L
AI Fabric | P-05 / 10 | Context is budgeted per request | Missing | None. | No context budget allocator; no max_input_tokens enforcement. | P1 | M
AI Fabric | P-06 / 19 | Cache before inference (L1-L4) | Missing | None; cache matches in ai-cost.ts are comments. | No exact, semantic or artifact cache; no invalidation keys. | P1 | L
AI Fabric | P-07 | Private model before frontier | Missing | All tiers map to external models via env vars. | No private inference, no vLLM adapter. | P2 | XL
AI Fabric | P-08 / 27 | Data policy overrides model quality | Missing | No sensitivity field anywhere in src. | No ai_tenant_policy, no classification, no policy engine. BLOCKS Private and Sovereign AI as a product. | P0 | L
AI Fabric | P-09 / 51.12 | Application code uses model ALIASES only | Missing | Hard-coded in bim/agent, cad/agent, cad/assistant routes and jobs.ts lines 65-67. | Replace concrete model names with registry-resolved aliases. | P1 | S
AI Fabric | P-10 / 20 | Every AI call has economics attribution | Partial | ai_job carries tenant, project, tier, model, tokens, cost_minor, trace_id, prompt_ref. | One row per JOB not per ATTEMPT; retry overwrites tokens so failed-attempt spend is invisible. | P0 | S
AI Fabric | 29 | ai_job table | Done | ai_job with idempotency_key, leases, backoff, reconciler. | Richer than the blueprint sketch. | P0 | -
AI Fabric | 29 | ai_usage_ledger (immutable per-attempt) | Missing | Fields live on ai_job but are mutable. | Append-only ledger; one row per execution attempt. | P0 | S
AI Fabric | 29 | ai_tenant_policy | Missing | None. | Required for enterprise deployment tiers. | P0 | M
AI Fabric | 29 / 18 | ai_prompt_version (prompt registry) | Missing | Prompts are strings in worker/src/prompts.mjs. | Section 18 forbids untracked prompt strings in source. | P1 | M
AI Fabric | 29 / 14 | ai_model_registry | Missing | Models are env vars with hard-coded fallbacks. | Needed for alias indirection, rate cards, licence metadata. | P1 | M
AI Fabric | 29 | ai_artifact | Done | artifact plus artifact_provenance plus artifact_type with JSON-schema validation. | Named differently, functionally stronger. | P0 | -
AI Fabric | 21 | Cost, token and latency guardrails | Missing | None. | Router must reject or re-route when a budget would be exceeded. | P1 | M
AI Fabric | 16 | Composite confidence and escalation | Partial | bim/eval.ts scores selection; confidence on artifacts. | No composite confidence from retrieval strength plus rule agreement; no escalation ladder. | P2 | M
AI Fabric | 33 | Evaluation framework and golden datasets | Partial | bim/eval.ts and ai-eval.test.ts (36 tests). | Covers tool selection only; no golden set for requirement extraction or classification. | P1 | M
AI Fabric | 35 | AI economics targets measurable | Missing | ai-cost.ts computes mean cost per real job. | Cannot measure cache-hit, no-LLM or frontier percentages since those paths do not exist. | P1 | M
AI Fabric | App.C | 18 ADRs (ADR-AI-001 to 018) | Missing | No docs/adr directory in the repo. | Write the six that unblock current work. | P1 | S
PCM | 5.1 | pcm_object | Done | pcm_object in 015_pcm_v1.sql. | - | P0 | -
PCM | 5.2 | pcm_object_type (data-driven) | Done | pcm_object_type. | - | P0 | -
PCM | 4.1 | pcm_spatial_node hierarchy | Done | pcm_spatial_node. | - | P0 | -
PCM | 17 | pcm_change_set and pcm_change_operation | Done | Both present; ChangeSet-based mutation. | - | P0 | -
PCM | 18 | Project revision and optimistic concurrency | Done | pcm_project_revision; pcm/store.ts. | - | P0 | -
PCM | 13 | pcm_relationship (typed edges) | Done | pcm_relationship. | - | P0 | -
PCM | 21 | Quantity results | Done | pcm_quantity; pcm/measure.ts. | - | P0 | -
PCM | 23 | BOQ object mapping | Done | pcm_boq_map. | - | P0 | -
PCM | 11 | Coordinate systems and source transforms | Done | pcm_coordinate_system, pcm_source_transform. | - | P1 | -
PCM | 7.1 | pcm_property_definition (typed schema) | Missing | Only pcm_property_value exists. | Values without definitions means no typing, units, validation or inheritance. | P1 | M
PCM | 6 | pcm_family and pcm_type (type-instance separation) | Missing | None. | No reusable wall or door types; blocks smart components. | P1 | L
PCM | 8 | Classification (IFC, Uniclass, MasterFormat) | Missing | None. | Blocks cost-code mapping, IFC fidelity and standards packs. | P1 | M
PCM | 12 | pcm_constraint and dependency graph | Missing | None. | No parametric recompute; Grid-Column-Beam chains impossible. | P2 | XL
PCM | 15.1 | source_region (document-region anchor) | Missing | artifact_provenance and trace endpoints exist, but no page or polygon anchor. | LINCHPIN GAP. Click-a-quantity-highlight-the-drawing is claimed in four documents and cannot work. | P0 | M
PCM | 43 | pcm_validation_result | Missing | validate.ts and standards.ts exist. | Validation runs but results are not persisted or queryable per object. | P2 | M
PCM | 49 | pcm_object_version | Missing | Change operations record before and after. | No per-object version rows; history only replayable. | P2 | M
PCM | 33 | Transactional outbox for events | Done | event_outbox and usage_outbox tables. | Verify consumers are idempotent. | P0 | -
PCM | 45 | Tenant isolation | Done | App-layer scoping; tenancy.test.ts and tenant-scoping.test.ts. | Doc suggests PostgreSQL RLS; MySQL has none so app-layer is the only line. | P0 | -
PCM | 34 | PostgreSQL and PostGIS as primary store | N/A | Implementation is MySQL 8. | DOCUMENT CONFLICT. PCM DDL uses JSONB and TIMESTAMPTZ (18 occurrences) that will not run on MySQL. | P0 | S
PCM | 65 | 12 ADRs (ADR-001 to 012) | Missing | None exist. | - | P1 | S
PCM | 66 | Stale quantities cannot masquerade as current | Partial | pcm_quantity has status; boq/reconcile.ts distinguishes verdicts. | Dirty-propagation pipeline not wired end to end. | P1 | M
DocLogix | 6 | Intelligent document register (35+ fields) | Missing | file and file_page tables only. | No controlled document register. This is the module core object. | P0 | L
DocLogix | 7 | Document numbering engine | Missing | None. | No numbering schemes, segment validation or duplicate detection. | P0 | M
DocLogix | 8 | Formal revision versus file version | Missing | None. | Construction revision semantics absent. | P0 | M
DocLogix | 9 | Revision intelligence (change classification) | Partial | cad/compare.ts diffs DXF revisions; cad/impact.ts classifies impact. | CAD only. No document or text revision comparison. | P1 | L
DocLogix | 10 | Configurable document workflow engine | Partial | workflow, workflow_run, workflow_run_step tables. | Generic workflow only; no document states, SLA, escalation or approval matrices. | P1 | L
DocLogix | 11 | Review and approval workspace | Missing | Persona review-queue endpoints exist. | No document review UI, markup, pinned comments or decision log. | P1 | L
DocLogix | 12 | Transmittal management | Missing | None. | Transmittals are a formal contractual record. Entirely absent. | P0 | L
DocLogix | 3 L4 | Document-to-everything connected intelligence | Missing | - | Depends on the register existing first. | P1 | XL
DocLogix | - | OCR and text extraction pipeline | Partial | CAD extraction service for drawings. | No OCR for scanned PDFs, Office formats or email capture. | P1 | L
DrawLogix | 10 | Drawing intake and recognition | Partial | cad_extraction, file_page, dwg2dxf sidecar, SVG render. | Extraction works; no symbol or object RECOGNITION producing candidate PCM objects with confidence. | P1 | XL
DrawLogix | 8 | Deterministic command set | Partial | bim/commands.ts, cad/tools.ts, ToolRegistry propose and apply. | No CreateSlab, Beam, Grid, Pipe, Duct; no CreateView, Sheet, Schedule. | P1 | L
DrawLogix | 9 | AI Design Copilot with execution modes | Done | bim/agent2.ts, cad/agent.ts, assistant route; propose, preview and apply honoured. | Matches the blueprint execution-mode model closely. | P0 | -
DrawLogix | 18 | ChangeSet states DRAFT to COMMITTED | Done | pcm_change_set and bim_proposal. | - | P0 | -
DrawLogix | 16 | Views, sheets, tags and schedules | Partial | bim/sheets.tsx and bim/documentation.ts (29 tests). | No live schedules as PCM projections, no revision clouds. | P2 | L
DrawLogix | 15 | Clash and coordination | Missing | None. | No federation, clash detection or issue workflow. | P2 | XL
DrawLogix | 11 | Native 2D and 3D authoring | Partial | cad/editor.tsx, bim/studio.tsx, viewport, iso views. | 2D present; no true 3D or BIM authoring, no parametric regeneration. | P2 | XL
DrawLogix | 21 | Interoperability PDF, DWG, DXF, IFC | Partial | DWG to DXF via LibreDWG; DXF round-trip; PDF pages. | No IFC import or export at all. IFC is required in three documents. | P1 | L
DrawLogix | 12 | Smart components and families | Missing | library_entry table exists. | No parametric component definitions with connectors or quantity rules. | P2 | L
DrawLogix Studio | 6 | Desktop client (Studio) | Partial | Electron shell; desktop.ts, desktopBuilds.ts, bundles.ts, renderer build. | No native geometry runtime, no local PCM cache, no GPU renderer. | P2 | XL
DrawLogix Studio | 9 | Offline working package and sync | Missing | None. | Offline is an architecture-level Studio requirement (Decision 8). | P2 | XL
DrawLogix Studio | 19 | Semantic conflict handling | Missing | Optimistic concurrency via project revision. | No semantic merge or conflict UI. | P2 | L
TenderLogix | 32 | Requirements extraction with clause citation | Missing | surfaces/tender.tsx and surfaces/specs.tsx exist as surfaces. | No requirement objects, evidence links or confirm workflow. This is the recommended FIRST AI proving workload. | P0 | L
TenderLogix | 32 | Compliance matrix | Missing | None. | Requirement to Evidence to Response to Approval to Submission chain absent. | P0 | L
TenderLogix | 42 | BOQ and quantity reconciliation | Done | boq/reconcile.ts with 27 tests; four verdicts; employer versus derived versus adopted. | Logic complete but NOT wired into the BOQ surface yet. | P1 | S
TenderLogix | 76 | Submission readiness and hard gate | Partial | submission.ts, lifecycle.ts, pursuit.ts. | Readiness exists; no hard blocker gate. | P1 | M
TenderLogix | 61 | Addendum intelligence | Missing | None. | Unincorporated addendum should be a hard submission blocker. | P1 | L
TenderLogix | 56 | Clarifications lifecycle | Missing | None. | - | P2 | M
TenderLogix | - | Tender War Room cockpit | Partial | surfaces/tender.tsx and project dashboards. | No countdown, readiness tiles or AI brief. | P2 | M
ScheduleLogix | 9 | Deterministic CPM engine | Done | cpm.ts: forward and backward pass, FS, SS, FF, SF, lag, float, critical path. | Strong; matches SL-P6-011, 012 and 013 intent. | P0 | -
ScheduleLogix | - | Programme storage and UI | Done | project_programme, programme/gantt.tsx, programme endpoints, xlsx export. | - | P0 | -
ScheduleLogix | 5 | P6 XER and XML migration | Missing | None. | RELEASE-BLOCKING per the document (SL-P6-001 and 002). | P1 | XL
ScheduleLogix | App.B | Migration reconciliation and confidence score | Missing | None. | - | P1 | L
ScheduleLogix | 11 | Baselines and schedule versions | Missing | None. | Baseline and compare is P0 (SL-P6-023 and 024). | P1 | L
ScheduleLogix | 8 | Calendars (global, project, resource) | Missing | None. | P0 (SL-P6-009). CPM without calendars cannot match P6. | P1 | L
ScheduleLogix | 14 | Resources, cost loading and earned value | Missing | None. | P1 tier (SL-P6-033 to 036). | P2 | XL
ScheduleLogix | 13 | Work readiness score | Missing | None. | Differentiator; depends on connected data. | P2 | L
ScheduleLogix | 16 | Delay intelligence and recovery scenarios | Missing | None. | Named the key differentiator. | P2 | XL
Knowledge Graph | Core | Typed relationship edges with provenance | Partial | pcm_relationship carries source and confidence. | PCM-scoped only; no cross-module edges. | P1 | L
Knowledge Graph | Impact | Change impact engine | Partial | cad/impact.ts: affected, unaffected and unknown verdicts. | CAD to measurement only; no traversal to BOQ, cost, schedule, procurement or RFI. | P1 | XL
Knowledge Graph | APIs | Graph traversal APIs | Missing | pcm/objects/[oid]/trace exists. | No neighbors, lineage or downstream-impact endpoints. | P2 | L
Knowledge Graph | Roadmap | Phase 1 DocLogix and TenderLogix relationships | Missing | - | Blocked: DocLogix has no register to relate to. | P1 | L
Master | 45.1 | No module calls external AI providers directly | Done | Verified across src/app/api. | - | P0 | -
Master | 45.2 | No AI output silently becomes an approved fact | Done | Review queues, confirm and reject, deviation approve and reject. | - | P0 | -
Master | 45.4 | No formal revision overwritten without version and audit | Done | audit_event plus audit_chain hash chain plus /audit/verify. | Tamper-evident audit genuinely implemented. | P0 | -
Master | 45.7 | No AI answer retrieves another tenant data | Done | Tenant scoping on every query; dedicated tests. | - | P0 | -
Master | 45.12 | No critical workflow unusable if AI provider is down | Partial | Deterministic engines run independently. | Not tested; no degraded-mode test proves the claim. | P1 | S
Master | 6.1 | Reference stack (.NET 9, PostgreSQL, NATS) | N/A | Implementation: Next.js 15.5, TypeScript, MySQL 8, MySQL-backed queue. | DOCUMENT CONFLICT with AI Fabric section 3 and PCM section 34. Three stacks across three documents. | P0 | S
Master | 44 | 20 platform ADRs | Missing | No docs/adr directory. | 50 ADRs specified across three blueprints; zero exist. | P1 | M
Master | App.F | PRA / Engineering Bible source of truth | Missing | Not present in Documents folder. | The document the hierarchy depends on does not exist. | P0 | M
Master | 19 | Integration Hub and connector SDK | Missing | integrations.ts is stub-level. | No connector runtime, canonical mapping or reconciliation engine. | P2 | XL
Master | 28 | Domain event catalog | Partial | event_outbox exists. | No published event catalog or schema versioning. | P1 | M
Master | 33 | Observability and FinOps | Partial | log.ts request ids and redaction; ai-cost.ts; trace_id on ai_job. | No OpenTelemetry, metrics endpoint or dashboards. | P1 | M
Master | 36 | Testing strategy | Done | 426 tests across 23 files; Playwright golden path; static-analysis tests. | Strong coverage but see the CI gap. | P0 | -
Master | 52 | Definition of Done per feature | Partial | Most items met for shipped features. | No written DoD checklist enforced at review. | P2 | S

## Enterprise Readiness
Enterprise readiness controls
What an enterprise buyer, a security review or a procurement questionnaire will ask for.
Category | Control | Status | Evidence | What is needed | Priority
Security | Multi-tenant isolation | Done | App-layer scoping on every query; tenancy + tenant-scoping tests. | Keep the static-analysis test that proves no unscoped query ships. | P0
Security | Tamper-evident audit trail | Done | audit_event + audit_chain hash chain; /api/v1/audit/verify. | - | P0
Security | Auth rate limiting | Done | better-auth rateLimit on /sign-in/email (auth.ts:34). | - | P0
Security | RBAC / permissions | Done | tenant_role, tenant_permission, tenant_role_permission, user_role; iam.ts. | - | P0
Security | SSO (SAML / OIDC) | Missing | None. | Enterprise deal blocker. Required by Master sec.6.1 and Complete Platform sec.15. | P0
Security | MFA | Missing | Only i18n strings; no implementation. | Required by Complete Platform sec.15. | P0
Security | SCIM user provisioning | Missing | None. | Expected by large enterprises alongside SSO. | P1
Security | Encryption at rest / KMS abstraction | Missing | No app-level encryption or key management. | Required by Complete Platform sec.15 and AI Fabric sec.28.2. | P0
Security | Secrets management (Vault/KMS) | Missing | Secrets via .env on the host. | AI Fabric sec.28.2 requires a secret-manager abstraction. | P1
Security | Credential rotation (previously committed secrets) | Missing | Outstanding from the earlier security review. | Rotate everything ever committed; move off default DB password. | P0
Security | Upload malware scanning | Missing | None. | Required by Complete Platform sec.15 and PCM sec.16. | P1
Security | Prompt-injection defence | Partial | Tools are data, not code; no eval path; proposals need approval. | No explicit separation of trusted instructions from retrieved evidence (AI Fabric sec.28.3). | P1
Security | Data residency / regional storage | Missing | Single VPS. | Enterprise requirement for GCC customers. | P1
Security | Retention and legal hold | Missing | None. | Required by Complete Platform sec.15. | P1
Ops | CI running the test suite | Missing | Six workflow files exist; none has ever executed (PAT lacks workflow scope). | 426 tests and six quality gates run only on a developer machine. HIGHEST-LEVERAGE FIX. | P0
Ops | Automated backup and restore | Missing | No backup automation or tested restore. | Master Epic 10 and Complete Platform sec.15. Untested restore is not a backup. | P0
Ops | Observability (OpenTelemetry, metrics) | Partial | Structured logs with request ids and redaction; trace_id on ai_job. | No OTel, no metrics endpoint, no dashboards or alerting. | P1
Ops | Health checks | Done | /api/healthz; docker compose healthchecks. | - | P0
Ops | Durable job queue with recovery | Done | job-queue.ts: conditional-UPDATE claims, leases, backoff, reconciler; 21 tests. | - | P0
Ops | Deploy repeatability | Done | deploy.ps1 with sha256-verified resumable upload; migrations; catalog seed gate. | - | P0
Ops | Zero-downtime / rollback | Missing | docker compose up recreates containers. | No blue-green, no tested rollback path. | P1
Ops | Environment separation (staging) | Missing | Production only. | Changes are validated in production. Needed before enterprise SLAs. | P0
Ops | Dependency vulnerability management | Partial | next 15.5.23 and postcss 8.5.26 patched; 9 advisories remain, all dev-only or unreachable. | Automate: no CI means Dependabot findings are triaged by hand. | P1
Ops | Port exposure hardening | Partial | 3308, 4000, 8081 bind to 127.0.0.1 and are externally closed. | 3307 (host MySQL), 11434 (Ollama, unauthenticated), 5000 bind 0.0.0.0; only the provider firewall stops them. | P0
Ops | Branch protection / PR review | Missing | autosync commits directly to main. | No review gate on production code. | P0
Compliance | SOC 2 / ISO 27001 readiness | Missing | Audit trail exists; no control framework, evidence collection or policies. | Named in Complete Platform sec.15 as a target. | P1
Compliance | DPA / data processing records | Missing | None. | Required for enterprise procurement. | P1
Compliance | AI governance (model approval, supply chain) | Missing | No model registry, licence records or approval workflow. | AI Fabric sec.28.5. | P1
Product | Accessibility WCAG 2.2 AA | Done | Semantic tokens with computed contrast; design-system.test.ts (24 tests). | - | P1
Product | Internationalisation (EN, AR, FR) | Done | i18n/en, ar, fr; logical CSS properties for RTL. | - | P1
Product | Light / dark / system theming | Done | globals.css alias layer; system bootstrap in layout.tsx. | - | P1
Product | Desktop client | Partial | Electron shell with bundled renderer; signed installers served from /desktop. | No auto-update channel, crash reporting or enterprise deployment support. | P2
Product | Entitlements and packaging | Done | entitlement_snapshot, entitlements.ts, modules.ts. | - | P1
Product | Export and exit (no lock-in) | Partial | BOQ csv/xlsx, programme xlsx, narrative md, DXF round-trip. | No full-project structured export; ScheduleLogix requires a P6-compatible export. | P1

## Document Conflicts
Where the documents contradict each other
Master Blueprint Appendix F states child documents must not silently contradict it. These already do.
Topic | Document A says | Document B says | The conflict | Why it matters | Resolution
Primary database | Master Blueprint sec.6.1 - PostgreSQL | AI Fabric sec.3 - MySQL 8 | Two blueprints name different primary stores. | PCM DDL uses JSONB and TIMESTAMPTZ (18 occurrences) which will not execute on MySQL. An engineer implementing PCM literally produces code that does not run. | Write one ADR fixing MySQL 8; amend PCM DDL and Master sec.6.1.
Primary API runtime | Master Blueprint sec.6.1 - .NET 9 | AI Fabric sec.3 - Node 20 / Next.js 15 | Different application runtimes. | Reality is Next.js 15.5. Master sec.6.1 is unimplementable without a rewrite. | Amend Master sec.6.1 to record the actual runtime.
Queue and broker | AI Fabric sec.3 and 31 - Redis + arq | Implementation - MySQL-backed queue | Doc prescribes a broker the system does not use. | MySQL queue gives durability and idempotency in the same database as authoritative state; Redis would add a component that can lose jobs on restart. | Amend the document, not the code. Record as an ADR.
AI execution language | AI Fabric sec.3 - Python 3.11 / FastAPI | Implementation - Node worker (worker/src/*.mjs) | Doc prescribes a Python service. | The CAD sidecar IS Python; the AI worker is Node. Mixed, and neither matches the doc. | Decide deliberately and record it.
Spatial queries | PCM sec.10 - PostGIS recommended | Implementation - MySQL spatial | Different spatial engines. | Affects geometry query design if 3D or complex spatial predicates are needed later. | Resolve with the database ADR.
Tenant isolation mechanism | PCM sec.45 - PostgreSQL RLS for defence in depth | Implementation - app-layer only | MySQL has no RLS. | Already acknowledged in tenancy.test.ts. App layer is the only line of defence. | Keep the static-analysis test as the compensating control; note it in the ADR.
Vector store | Master sec.6.1 - pgvector first | Implementation - chunk table with JSON embedding | Different vector strategy. | chunk exists but nothing reads or writes it, so neither approach is live. | Decide when retrieval is actually built.
Source of truth hierarchy | Master App.F - PRA / Engineering Bible is authoritative | Documents folder - no PRA exists | The authoritative document is missing. | Nothing arbitrates between blueprints, which is why three stacks coexist unresolved. | Write the PRA or demote the reference so the hierarchy is honest.

## Roadmap
What to do next - P0 only, sequenced
Ordered so each step unblocks the next. Effort: S = days, M = 1-3 weeks, L = 1-2 months, XL = a quarter with a team.
# | Action | Why now | Unblocks | Effort | Owner type
1 | Grant the PAT workflow scope so CI runs | 426 tests and six quality gates have never executed anywhere but a developer machine. Two production deploys today were verified by hand. | Every other item on this list, safely. | S | You - one setting
2 | Rotate all credentials ever committed; confirm the production DB password is not the default | Outstanding from the earlier security review. MySQL on 3307 binds 0.0.0.0 and is stopped only by the provider firewall. | Any security questionnaire. | S | You + engineering
3 | Add per-attempt AI usage ledger | ai_job holds one mutable row per job, so a retry overwrites the previous attempt tokens. AI cost is under-counted by exactly the failed attempts, which are the expensive ones. | All FinOps targets; the cost-optimisation loop; any margin claim. | S | Engineering
4 | Write the database ADR and reconcile the documents | Three blueprints name three different stacks. PCM DDL uses JSONB and TIMESTAMPTZ that cannot run on MySQL. | Anyone implementing PCM from the document without producing broken code. | S | Architecture
5 | Branch protection and a staging environment | autosync commits straight to main and changes are validated in production. | Enterprise SLA conversations. | M | Engineering
6 | Automated backup with a tested restore | There is no backup automation and no proven restore. | Pilot acceptance (Master Appendix E item 7). | M | DevOps
7 | ai_tenant_policy plus a data-sensitivity model | Nothing prevents confidential tender pricing reaching an external model, because no code knows data has a classification. | Preckon Private AI and Sovereign AI as sellable products. | L | Engineering
8 | SSO (SAML/OIDC) and MFA | Both are named in Complete Platform sec.15 and neither exists. Enterprise deal blockers. | Enterprise procurement. | L | Engineering
9 | source_region document-region provenance anchor | Click-a-quantity-and-highlight-the-drawing is claimed in four documents and cannot work without it. It is the moat those documents describe. | Quantity defensibility; DocLogix and DrawLogix traceability. | M | Engineering
10 | DocLogix register, numbering, revisions, transmittals | DocLogix is positioned as the CDE backbone and is the Knowledge Graph Phase 1 dependency, yet has no controlled document object at all. | Knowledge Graph; TenderLogix compliance; the connected-lifecycle claim. | XL | Team
11 | TenderLogix requirements extraction with clause citation | AI Fabric sec.46 names this the recommended first AI proving workload. Needs retrieval (item 12) under it. | Compliance matrix; tender-to-BOQ; the AI value story. | L | Team
12 | Make the chunk table live - ingestion, chunking, retrieval | chunk exists with an embedding column and a FULLTEXT index, and nothing reads or writes it. Retrieval is scaffolding. | Requirements extraction; grounded project Q&A; token economics. | L | Team

## Built Inventory
What actually exists - raw evidence
Counted from the repository, not from the documents.
Area | Count / detail | Notes
Database tables | 56 | Includes 12 pcm_* tables, artifact + provenance + audit chain, event_outbox.
PCM tables | 12 | object, object_type, spatial_node, change_set, change_operation, project_revision, relationship, property_value, quantity, boq_map, coordinate_system, source_transform.
API routes | 78 | Next.js App Router route.ts handlers under src/app/api.
Module surfaces | 10 | boq, drawings, estimate, narrative, procurement, schedule, specs, tender, common, generic.
Tests | 426 passing, 23 files | Plus Playwright golden-path E2E. One pre-existing failure needs Docker MySQL on 3308.
Deterministic engines | cpm.ts, pcm/measure.ts, boq/reconcile.ts, cad/compare.ts, cad/impact.ts, standards.ts, validate.ts | CPM supports FS/SS/FF/SF with lag, float and critical path.
AI surfaces | bim/agent2.ts, cad/agent.ts, cad/assistant, bim/tools, authored tools | Generic ToolRegistry serving both BIM and CAD document types.
Locales | 3 (en, ar, fr) | Logical CSS properties for RTL; technical content not mirrored.
Deployed versions | next 15.5.23, postcss 8.5.26 | Verified inside the running container, not just the lockfile.
Open advisories | 9 | All dev-only (vitest, vite) or unreachable (sharp - next/image is unused).
CI runs | 0 | Six workflow files exist; none has ever executed.
ADRs | 0 | 50 are specified across three blueprints.