## Programme
Ref No: QO/17/26
PROJECT WORK PROGRAMME
Project No. | 17 |  |  |  | Location
Project | Spark |  |  |  | Submission | 24 June 2026
Client |  |  |  |  | Duration | 420 calendar days
No. | Activity | SOW Ref | Duration | Start | Finish | Predecessors
[7 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
Site Preparation & Demolition (Wk 4-10)
1 | Demolition & removal of existing water supply pipework | 7 | 21 | 22Jul26 | 12Aug26 | bar: W4 to W7
2 | Site clearance, excavation & blinding to foundations | 1 | 28 | 12Aug26 | 09Sep26 | 1 | bar: W7 to W11
Substructure (Wk 11-17)
3 | Reinforced concrete raft/pad foundations, ground beams | 1 | 49 | 09Sep26 | 28Oct26 | 2 | bar: W11 to W18
4 | Structure Topped-Out |  | — | 28Oct26 |  | 3 | bar: W18